## Product Backlog
E-Commerce Application — Product Backlog
Features ranked by business value — Very High → Very Low
# | Feature / Service | Category | Priority | Business Value | Effort (Sprints) | Assigned Release | Notes
1 | User Registration & Authentication | Core | Very High | ★★★★★ | 2 | Release 1.0 | OAuth + email/password
2 | Product Catalogue & Search | Core | Very High | ★★★★★ | 3 | Release 1.0 | Full-text search + filters
3 | Shopping Cart | Core | Very High | ★★★★★ | 2 | Release 1.0 | Persistent across sessions
4 | Secure Checkout & Payment Gateway | Core | Very High | ★★★★★ | 3 | Release 1.0 | Stripe / PayPal integration
5 | Order Management | Core | Very High | ★★★★★ | 2 | Release 1.0 | Create, track, cancel orders
6 | User Profile & Address Book | Account | High | ★★★★☆ | 1 | Release 1.0 | Multiple shipping addresses
7 | Email Notifications | Engagement | High | ★★★★☆ | 1 | Release 1.0 | Order confirm, shipping alerts
8 | Inventory Management (Admin) | Admin | High | ★★★★☆ | 2 | Release 1.0 | Stock levels & alerts
9 | Product Reviews & Ratings | Social | High | ★★★★☆ | 2 | Release 2.0 | Verified purchase reviews
10 | Wishlist / Save for Later | Engagement | High | ★★★★☆ | 1 | Release 2.0 | Shareable wishlists
11 | Discount Codes & Coupons | Marketing | Medium | ★★★☆☆ | 2 | Release 2.0 | % and fixed discounts
12 | Loyalty / Rewards Programme | Marketing | Medium | ★★★☆☆ | 3 | Release 2.0 | Points accumulation system
13 | Advanced Analytics Dashboard | Admin | Medium | ★★★☆☆ | 2 | Release 2.0 | Sales, traffic, conversion KPIs
14 | Multi-language & Currency Support | Global | Medium | ★★★☆☆ | 3 | Release 2.0 | i18n framework
15 | Live Chat Support Widget | Support | Medium | ★★★☆☆ | 2 | Release 2.0 | Intercom / Zendesk
16 | Product Comparison Tool | Discovery | Low | ★★☆☆☆ | 2 | Release 3.0 | Side-by-side comparison
17 | Subscription / Auto-replenish | Revenue | Low | ★★☆☆☆ | 3 | Release 3.0 | Recurring billing
18 | Social Login (Google, Facebook) | Account | Low | ★★☆☆☆ | 1 | Release 3.0 | OAuth social providers
19 | Affiliate & Referral Programme | Marketing | Low | ★★☆☆☆ | 2 | Release 3.0 | Commission tracking
20 | Gift Cards & E-vouchers | Revenue | Low | ★★☆☆☆ | 2 | Release 3.0 | Digital delivery
21 | AR Product Preview | Innovation | Very Low | ★☆☆☆☆ | 5 | Release 3.0 | WebAR / 3D model viewer
22 | AI-Powered Recommendations | AI | Very Low | ★☆☆☆☆ | 4 | Release 3.0 | Collaborative filtering
23 | Progressive Web App (PWA) | Mobile | Very Low | ★☆☆☆☆ | 3 | Release 3.0 | Offline support
24 | Dark Mode UI | UX | Very Low | ★☆☆☆☆ | 1 | Release 3.0 | CSS theme toggle
25 | Voice Search | Innovation | Very Low | ★☆☆☆☆ | 3 | Release 3.0 | Web Speech API

## Product Roadmap
E-Commerce Application — Product Roadmap
Release | Duration | Sprints | Priority Focus | # Features | Total Effort | Key Features (Top 5) | Description | Status
Release 1.0 | 6 months | 10 | Very High, High | 8 | 16 sprints | • User Registration & Authentication • Product Catalogue & Search • Shopping Cart • Secure Checkout & Payment Gateway • Order Management | Foundation — core shopping experience | 🟢 In Progress
Release 2.0 | 4 months | 7 | High, Medium | 7 | 15 sprints | • Product Reviews & Ratings • Wishlist / Save for Later • Discount Codes & Coupons • Loyalty / Rewards Programme • Advanced Analytics Dashboard | Growth — engagement & marketing tools | 🔵 Planned
Release 3.0 | 6 months | 10 | Low, Very Low | 10 | 26 sprints | • Product Comparison Tool • Subscription / Auto-replenish • Social Login (Google, Facebook) • Affiliate & Referral Programme • Gift Cards & E-vouchers | Scale — innovation & global reach | ⚪ Backlog

## Timeline
E-Commerce Application — Release Timeline
Release / Feature | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16
Release 1.0 (Months 1–6) | bar: Month 1 to Month 6
User Registration & Auth | bar: Month 1 to Month 2
Product Catalogue & Search | bar: Month 1 to Month 3
Shopping Cart | bar: Month 2 to Month 3
Checkout & Payment | bar: Month 3 to Month 5
Order Management | bar: Month 5 to Month 6
User Profile & Address | bar: Month 2 to Month 3
Email Notifications | bar: Month 4 to Month 5
Inventory Mgmt (Admin) | bar: Month 4 to Month 6
Release 2.0 (Months 7–10) | bar: Month 7 to Month 10
Product Reviews & Ratings | bar: Month 7 to Month 8
Wishlist / Save for Later | bar: Month 7 to Month 8
Discount Codes & Coupons | bar: Month 8 to Month 9
Loyalty / Rewards | bar: Month 8 to Month 10
Analytics Dashboard | bar: Month 9 to Month 10
Multi-language & Currency | bar: Month 9 to Month 10
Live Chat Support | bar: Month 9 to Month 10
Release 3.0 (Months 11–16) | bar: Month 11 to Month 16
Product Comparison Tool | bar: Month 11 to Month 12
Subscription / Auto-replen | bar: Month 11 to Month 13
Social Login | bar: Month 11 to Month 12
Affiliate Programme | bar: Month 12 to Month 13
Gift Cards | bar: Month 12 to Month 13
AR Product Preview | bar: Month 13 to Month 16
AI Recommendations | bar: Month 13 to Month 15
PWA | bar: Month 14 to Month 15
Dark Mode | bar: Month 15 to Month 16
Voice Search | bar: Month 14 to Month 16